**REQUEST FOR QUOTATION  
TIME SCHEDULE FOR THE RFQ/PROCUREMENT PROCESS**

**PROCUREMENT OF CONSTRUCTION MATERIALS FOR TAMANA ISLAND COUNCIL PROJECT**

**Procurement No:** **09-G009-23**

Time Schedule for the RFQ/procurement process

The Procurement will follow the timeline below for this RFQ. Any changes to this timeline will be posted on the MFED/CPU Portal (<http://procurement.gov.ki>) or sent to directly Tenderers who have been specifically invited to submit a Tender. Please note that the dates set forth in 6-11 are target dates and may be adjusted.

|  |  |  |
| --- | --- | --- |
| **Event** | **Responsible Party** | **Date and time, KST\*** |
| 1. Launch and publication of RFQ | OB | 24/11/2023 |
| 1. Last date for questions about RFQ | Tenderer | 29/11/2023 |
| 1. Last date for answers to questions and/or to amend the RFQ | OB | 30/11/2023 |
| 1. Last date for submission of Quotation | Tenderer | 4/12/2023 at 5.15pm |
| 1. Evaluation finalized | OB | 06/12/2023 |
| 1. Award of Contract | OB | 08/12/2023 (Online discussion) |
| 1. Contract finalization | OB/Tenderer | 12/12/2023 |
| 1. Contract signing | OB/Tenderer | 24/12/2023 |
| 1. Contract/Project start date | Tenderer | OB will arrange the delivery of materials |

\* Kiribati Standard Time (Tarawa Time) GMT+12 – Quotations or Questions, or parts thereof, delivered after the latest date and time for submission will not be opened or considered.

\*\* [The Procuring Entity] may decide to give a presentation of the Specification

\*\*\* Presentation opportunity may be given, and if so, to qualified Tenderers only