**REQUEST FOR PROPOSAL  
TIME SCHEDULE FOR THE RFP/PROCUREMENT PROCESS**

**Procurement No:** **RFP-22-W001-25**

### Time Schedule for the RFP/procurement process

The Procurement will follow the timeline below for this RFP. Any changes to this timeline will be posted on the Kiribati Public Procurement WebPortal (www.procurement.gov.ki/opentender) or sent directly to Tenderers who have been specifically invited to submit a Tender. Please note that the dates set forth in 6-11 are target dates and may be adjusted.

|  |  |  |
| --- | --- | --- |
| **Event** | **Responsible Party** | **Date and time, KST\*** |
| 1. Launch and publication of RFP | Procuring Entity | 09/09/25 |
| 1. Specification presentation\*\* | Tenderer | 12/09/25 |
| 1. Last date for questions about RFP | Tenderer | 17/09/25 (17:00) |
| 1. Last date for answers to questions and/or to amend the RFP | Procuring Entity | 18/09/25 |
| 1. Last date for submission of Proposals | Tenderer | 19/09/25 (17:00) |
| 1. Proposal presentation\*\*\* | Tenderer | 23/09/25 |
| 1. Evaluation finalized | Procuring Entity | 24/09/25 |
| 1. Award of Contract | Procuring Entity | 25/09/25 |
| 1. Contract Terms and Conditions | Procuring Entity/Tenderer | 09/10/25 |
| 1. Contract signing | Procuring Entity/Tenderer | 13/10/25 |
| 1. Contract/Project start date | Tenderer | 14/09/25 |

\* Kiribati Standard Time (Tarawa Time) GMT+12 – Proposals or Questions, or parts thereof, delivered after the latest date and time for submission will not be opened or considered.

\*\* The Procuring Entity may decide to give a presentation of the Terms of Reference

\*\*\* Presentation opportunity may be given, and if so, to qualified Tenderers only